## Introduction
The Council and Amey are continuing to progress the programme of outstanding surfacing works from the Core Investment Programme (the first five years) of the Streets Ahead PFI contract. This update (2nd tab) confirms we have 30 roads where work is outstanding. We’ve also given an indication of which year we anticipate the works to be progressed. Some of the outstanding roads present a number of challenges in developing options to retain mature trees whilst ensuring we provide accessible, safe footpaths and roads. Working alongside the Sheffield Street Tree Partnership, we remain committed to providing a clear and transparent process for the council’s design recommendations.

## Street Status (78 Streets)
Street No | Street Name | Ward | No of Trees Impacting Highway (Identified in CIP) | Current Status | Remedial Works Undertaken | Status | Update Feb 23 | Programme Year
1 | ABBEYDALE PARK RISE | Dore & Totley | 11 | Closed | Works Completed, Street Resurfaced in 2020 | A | Completed | Completed
2 | AGDEN ROAD | Central | 2 | Closed | Kerbstones in front of the tree were missing and had been replaced with Asphalt. With excessive Asphalt removed from around the tree and kerb line. Arborists removed minor roots from the kerb line. The kerb was rebuilt with kerbstones and stone setts. Roots were protected with membrane. A larger tree pit was created with wooden formers. Asphalt was laid and tree pit filled with bark chippings. Outstanding works still to be designed for the tree outside 3-5 as of October 2021. | A | Completed | Completed
3 | ALBANY ROAD | Central | 2 | Closed | Remedial works undertaken during joint inspection with a number kerbstones realigned, tree pits constructed. However outstanding works remain to Carriageway and Footways. Relaxation to contractual standards agreed. | A | Completed | Completed
4 | ALDAM ROAD | Dore & Totley | 3 | Design Solution Outstanding | Neither footway or carriageway surfacing has been concluded to date, with a number of defects not addressed during joint inspections. | B | Requires design solutions & build | 23/24
5 | ALDAM WAY | Dore & Totley | 1 | Closed | Tree Condition issue addressed | A | Completed | Completed
6 | ALDFIELD WAY | Burngreave | 1 | Closed | Single lane, estate road with mature tree in footway creating an obstruction, preventing safe passage between the tree and property boundary. Footway ramped due to buttress root. Refer to Options Review. Road safety view sought. As a historical layout with a single isolated tree, with alternative crossing points at Edensor and Fairbank Roads available with a low upstand on the kerbs, the road is accessible for impaired highway users. Therefore, the recommendation is to retain the tree with no alterations to the highway required. | A | Completed | Completed
7 | ALDRED ROAD | Crookes | 1 | Closed | During joint inspections, old asphalt overlays and sunken kerbstones were removed. Some small roots were pruned. Kerbs were cut to size and reset. Stone flags were shaved underneath to lay flat over roots. An enlarged tree pit was created to accommodate surface roots. Pit was mulched to finish. Both Carriageway and Footway surfacing completed | A | Completed | Completed
8 | ARGYLE ROAD | Gleadless Valley | 1 | Closed | No Joint Inspections, works undertaken alongside Meersbrook Park Road, concluded 2020. With carriageway defect addressed. No further action | A | Completed | Completed
9 | BANNER CROSS ROAD | Ecclesall | 9 | Design Solution Outstanding | The Council will now progress to a resident consultation to seek views on the engineering works required to retain the trees and assosciated loss of parking for this street | D | Requires design solutions & build | 23/24
10 | BINFIELD ROAD | Gleadless Valley | 5 | Closed | Investigations and remedial works completed 2020, no joint inspections undertaken. Amey committed to address and fund remedial works for War Memorial Streets, both footway and carriageway surfacing planned for 2021 | A | Completed | Completed
11 | BRIAR ROAD | Nether Edge | 3 | Closed | Through the joint inspections, thinner kerbs were installed and tree pits created, with historic mounding of asphalt removed. Both carriageway and footway have been resurfaced | A | Completed | Completed
12 | BRINCLIFFE GARDENS | Nether Edge | 1 | Closed | Joint Inspection - Defects addressed with the kerbstone in front of the tree removed and the kerb trough cleared to check for roots. No roots were in the kerb line so the kerbstone was just settled back into place. Carriageway surfacing concluded, footway surfacing planned 2021 | A | Completed | Completed
13 | CHATSWORTH ROAD | Dore & Totley | 1 | Closed | Remedial works undertaken, installing kerbs and edges that meet the relaxed specification with increased monitoring and maintenance which facilitate resurfacing works. Carriageways completed. Footway completed Feb 2021 | A | Completed | Completed
14 | CHELSEA ROAD | Nether Edge | 2 | Closed | The crew lifted the kerb line to allow the roadway to ramp over the roots. Cobbles were removed to allow depth for a layer of concrete under asphalt, as the roots were coming through the gaps between the cobbles, with a thin layer of asphalt on top which had worn away. Some roots were pruned but one big one can't be cut. A layer of sand to allow the roots room to grow if they need it, with a 4 inch layer of concrete on top before asphalt laid. Pavement resurfaced. Tree was pruned on 14th January 2020. Outstanding - Surfacing to the junction of Union Road, overlay required due to rooting in the Carriageway, kerb height raised to allow for surfacing. | A | Compleed | Completed
15 | CHIPPINGHOUSE ROAD | Nether Edge | 2 | Design Solution Outstanding | Extend tree pits on the footway and resufacing Accept missing kerbs as a no cost option to minimise impact on the street scene | B | Requires design solutions | 23/24
16 | CLIFFEFIELD ROAD | Gleadless Valley | 1 | Design Solution Outstanding | The Council will now progress to a resident consultation to seek views on the engineering works required to retain the trees and potential tree replacements for this street | B | Requires design solutions & build | 24/25
17 | COVERDALE ROAD | Nether Edge | 1 | Closed | Single build out to be constructed | A | Completed | Completed
18 | CRAWFORD ROAD | Gleadless Valley | 1 | Closed | Remedial works undertaken, during joint inspection, concluding with a new concrete kerb, cast in situ. A further visit repaired the surface, chamfered the cast kerb and mulched the new tree pit | A | Completed | Completed
19 | CRESCENT ROAD | Nether Edge | 1 | Design Solution Outstanding | No joint Inspections undertaken. Defects on footway only, extending tree pits required, to be concluded 2021. Carriageway previously completed and Footway in reasonable condition. | C | Requires design solutions & build | 23/24
20 | CRUISE ROAD | Fulwood | 1 | Closed | Tree was felled to a standing stem at approx. 2m in 19/10/2017. Remainder of stem and stump were removed during the final resurfacing works. Job completed. No joint inspection carried out as tree already removed. | A | Completed | Completed
21 | DIXON DRIVE | Stocksbridge | 1 | Closed | Kerbs repaired and carriageway resurfaced, issue resolved. No joint inspection undertaken, no further works required. | A | Completed | Completed
22 | DOBCROFT ROAD | Ecclesall | 1 | Closed | Remedial works undertaken, installing kerbs and edges that meet the relaxed specification with increased monitoring and maintenance to facilitate resurfacing works. No joint inspections undertaken | A | Completed | Completed
23 | DUNKELD ROAD | Ecclesall | 3 | Consultation Commenced | The Council will now progress to a resident consultation to seek views on next steps for this street, including consulting on replacing the 4 Dawn Redwoods | B | Requires design solutions & build | 23/24
24 | EAST BANK ROAD | Arbourthorne | 1 | Closed | Remedial works undertaken , no kerb issues. Asphalt humped around the tree was removed and a new tree pit fitted with wooden formers. Tree mulched. | A | Completed | Completed
25 | ECCLESALL ROAD | Broomhill | 11 | Desin Solution Outstanding | Longer term strategic approach for the aesthetic and planting on this shop site to be undertaken. Tree outside 367 Replaced due to significant decline following public consultation outcome in favour of these works proceeding | C | Major scheme review required. | 24/25
26 | EDGEBROOK ROAD | Nether Edge | 1 | Design Solution Outstanding | No joint inspections undertaken. Carriageway works have been concluded, footway done with the exception of a patch required outside no 21. Construct tree pit and conclude footway works, OS 27 Edgebrook leads into Ladysmith Ave. Design solution still outstanding for the tree outside 28 as of October 2021 | C | Requires design solutions & build | 24/25
27 | EDGEDALE ROAD | Nether Edge | 8 | Solution Developed Delivery Programmed | During the joint inspections 7 out of 8 trees with associated defects have been addressed with the exception, tree o/s 3-11 Javelin House (facing junction with Edgemount Rd) Unable to surface over root level in footway. Solution developed to provide footway in front of tree, minor reduction in carriageway width. | D | Solution developed. On site early 2023 | 22/23
28 | GATEFIELD ROAD | Nether Edge | 2 | Closed | No joint Inspections undertaken. Only section of Abbey Road outstanding approx. 40m. 4 trees, to address with similar defects | A | Completed | Completed
29 | GLENTILT ROAD | Nether Edge | 1 | Closed | Kerbstones cut back to give a defined kerb line with only minor deviation from linear, no defects or trips present, new tree pit cut in footway, repairs complete. Footway and carriageway resurfacing completed | A | Completed | Completed
30 | GROVE AVENUE | Hillsborough | 1 | Solution Developed Delivery Programmed | The continued relaxation of current standards in relation to the missing kerbs. Reconstruct the footway including a tree pit. No change to the highway network proposed with the tree retained. | B | Footway patch required only. Delivery programmed early 2023. | 22/23
31 | HORNINGLOW ROAD | Firth Park | 2 | Closed | Remedial works undertaken, installing kerbs and edges that meet the relaxed specification with increased monitoring and maintenance which facilitated resurfacing works. No joint inspection undertaken. The work had already been carried out before the joint inspections were initiated. | A | Completed | Completed
32 | HUNTER HOUSE ROAD | Nether Edge | 9 | Design Soltion Outstanding | Remedial works undertaken during joint inspections, installing kerbs / edges where appropriate and addressing the footway issues. Engineering solutions will be proposed to overcome the issue at Psalter Lane junction. Consultation forthcoming on the potential of replacing the tree outside No. 155 | B | Requires design solutions & build | 23/24
33 | KENBOURNE ROAD | Nether Edge | 7 | Design Solution Outstanding | Site investigations were concluded May 2021, with inspections undertaken with participation from members of STAG and the community. Tree outside 26 agreed for replacement due to Ash Dieback and receieved 100% backing in the the public consultation for this. A further resident consultation is forthcoming on the potential to retain trees through a significant number of build outs and the impact on the streetscene from this. | B | Requires design solutions & build | 24/25
34 | KENWOOD PARK ROAD | Nether Edge | 15 | Solution developed, detail design required, delivery to be programmed. | Site investigation undertaken May 2021, to inform options, observed by member of STAG and the community. A resident consultation is forthcoming on the potential to retain trees through a significant number of build outs and the impact on the streetscene from this. Solution developed to provide continuous kerbline. | C | Requires design solutions & build | 23/24
35 | KENWOOD ROAD | Central | 7 | Solution developed, detail design required, delivery to be programmed. | Investigations were completed jointly with STAG observing in May 21 October 2021 Update: Designed solution still to follow from Amey | C | Requires design solutions & build | 23/24
36 | KHARTOUM ROAD | Broomhill | 2 | Closed | Remedial works undertaken, which facilitated footway resurfacing works. Flagstones displaced by tree roots. Uneven footway surface. Large root just 55mm under surface after flags lifted and asphalt removed. Not possible to prune root or lay thinner flagstones or shape flagstones sufficiently to provide level surface. Surface of footway therefore slightly raised using sand to cover root. Existing and new flagstones cut to required size and re-laid on newly raised surface. No work on kerbs required. Large tree pit formed by the flagstones, and then mulch laid. | A | Completed | Completed
37 | LADYSMITH AVENUE | Nether Edge | 10 | Design Solution Outstanding | No joint inspection undertaken. Carriageway works outstanding, a number of displaced kerbs due to buttress roots (6 trees), some kerbs addressed, likely to be rooting into the Carriageway. To compromise on standards, accepting missing kerbs, with an overlay solution to deliver the improvement to the condition of the carriageway. The footways require full reconstruction, hand excavation around the trees and construction of tree pits where required. | C | Requires design solutions & build | 24/25
38 | LEES HALL AVENUE | Graves Park | 3 | Closed | No Joint Inspections - Kerb replaced, carriageway and footway resurfaced | A | Completed | Completed
39 | LEES HALL ROAD | Graves Park | 3 | Closed | Kerb replaced, carriageway resurfaced, footway remains outstanding, to be considered with Lismore, Stanley and Upper Albert. Works planned 2021 | A | Completed | Completed
40 | LISMORE ROAD | Gleadless Valley | 2 | Closed | Through the joint inspections with STAG kerbs were reinstated, raised footway (ramping) addressed and tree pits installed. Carriageways have been completed, footways planned for 2021 | A | Completed | Completed
41 | LYDGATE LANE | Crookes | 1 | Closed | Crown reduction/retrenchment pruning undertaken to address structural issues in tree. To be retained with enhanced (annual) inspection. | A | Completed | Completed
42 | MARLCLIFFE ROAD | Hillsborough | 2 |  | No joint inspections undertaken. Two trees outside the school, this is the only remaining work outstanding, the remainder of the footways have been surfaced and the carriageway has been resurfaced. Both trees have roots visible in the kerb line, kerbs are missing and can not be reinstated. The continued relaxation of current standards in relation to the missing kerbs and reconstruct the footway with extended tree pits. No change to the highway network proposed, trees retained | C | Footway patch required only | 23/24
43 | MEERSBROOK PARK ROAD | Gleadless Valley | 14 | Closed | Design implemented, with a number of build outs, use of flexi pave, extended tree pits, statement was published and works concluded 2020/ early 2021 | A | Completed | Completed
44 | MILDEN ROAD | Hillsborough | 3 | Solution Developed Delivery Programmed | Throughout the street there are a total of 6 trees were defects exists, an additional 3 to those identified in the Core Investment Period. Replacement Status Cancelled. Street will be monitored due to Ash Dieback | D | Footways only to complete, delivery early 2023 | 22/23
45 | MILTON ROAD | Nether Edge | 3 | Design Solution Outstanding | No Joint Inspections undertaken, surfacing planned for 2021. Replacement Status Cancelled. The continued relaxation of current standards in relation to the missing kerbs and the reduced footway width. No change to the highway network proposed, trees retained. | C | Requires design solutions & build | 23/24
46 | MONTGOMERY ROAD | Nether Edge | 16 | Closed | No joint inspections undertaken, Carriageway works completed, Footway works completed 2021. The outstanding missing and misaligned kerb defects are addressed in the Options Review. Replacement status cancelled. Amey recommend relaxation of highway standards as the carraigeway surfacing has already been completed and future projects such as TCF for cycle infrastructure may well change the nature of this road in the future | A | Completed | Completed
47 | MYRTLE ROAD | Gleadless Valley | Design Solution Out+G49:H49standing | Closed | Remedial works undertaken, resurfacing works concluded, No joint investigation. No kerb work required. Tree located adjacent to a speed bump with a white line 'build out' marking. The trunk slightly grows over kerb. The pavement had been previously patched. One tree replaced subject to windblow. | A | Completed | Completed
48 | OXFORD STREET | Walkley | 4 | Design Solution Outstanding | No joint inspections undertaken. Carriageway and footways surfacing outstanding. Greater number of trees creating defects to footways and kerb displacement than previously identified during Core Investment Period. Amey committed to funding the remedial works on Memorial sites The continued relaxation of current standards in relation to the missing kerbs and the reduced footway width. Use of alternative materials where a kerb line may be feasibly reinstated using edgings and slim kerbs. Use of permeable surfacing to footway where required. Installation of a build out in section one where the extent of rooting is significant in the carriageway and likely to impede resurfacing. It should be of minimal width and length to maintain the availability of parking which is at a premium in the area. | B | Requires design solutions & build | 23/24
49 | PINGLE ROAD | Ecclesall | 1 | Closed | Remedial works undertaken, to facilitate resurfacing works in 2019. No joint investigation. A thin kerb had already been fitted in front of the buttress, but not as part of the joint investigations. | A | Completed | Completed
50 | PSALTER LANE | Nether Edge | 2 | Closed | Carriageway Done, however missing kerb and proximity of tree to crossing and junction raised in the Options review. The continued relaxation of current standards in relation to the missing kerbs. The epicormic basal growth should be routinely trimmed to ensure sightlines are not compromised at the junction for pedestrians. | A | Completed | Completed
51 | RAVEN ROAD | Nether Edge | 1 | Closed | Remedial works undertaken, which facilitated resurfacing works. Slightly misaligned kerbstones were removed, minor roots pruned, and narrower kerbstones reset. Tree pit tidied up, but not relined with timber as the asphalt on the footpath around the tree had already been done giving the tree pit an edging. | A | Completed | Completed
52 | RIVELIN VALLEY ROAD | Walkley | 5 | Closed | Surfacing of the carriageway and footway completed. No Joint Investigation but works were observed by STAG. Pavement was repaired using normal pavement works. A slight rise was put in to align with an existing ironwork. | A | Completed | Completed
53 | ROTHERHAM ROAD | Mosborough | 1 | Closed | Tree Issue, not associated with footway or carriageway defects and works completed with no joint inspection | A | Completed | Completed
54 | RUNDLE ROAD | Nether Edge | 17 | Closed | Site Design completed and submitted for Approval Aug'20, which followed previous joint inspections which corrected a number of kerbs defects, either reset, or replaced with edgings. Those unresolved were subject to design, with build outs and lining solutions implemented and concluded 2020. | A | Completed | Completed
55 | RUSTLINGS ROAD | Ecclesall | 1 | Closed | Remedial works undertaken, during joint inspections, misaligned kerbstones in front of the tree were removed and the kerb trench dug out. Two very small roots protruding into the kerb line were pruned. The kerbstones were cut in two longwise and were put back in to make a straight narrower kerb. A tree pit was dug by removing surrounding asphalt and adding wooden edging. Note, there was no buttress root protruding into the kerb line. | A | Completed | Completed
56 | RYLE ROAD | Nether Edge | 1 | Solution developed, delivery programmed | Remedial works undertaken on a number of trees during joint inspections. Footways completed on one side which has no trees present. Outstanding footway options to be considered. Resident consultation forthcoming on the potential loss of a section of footway and introduction of additional crossing point to retain all trees and ensure a permanent solution is in place by making a change to the highway network. Update Feb 23 - solution developed, delivery programmed. | D | Solution developed. On site early 2023 | 22/23
57 | SACKVILLE ROAD | Crookes | 1 | Closed | Remedial works undertaken, through joint inspection, surfacing completed, tree pit was dug out uphill of the tree to accommodate the large root that has grown in that direction. Kerbstones that were lower than the road surface were lifted to allow them more clearance over the downhill root. Narrow kerbstones were fitted in front of tree. Surfaced and mulch completed. | A | Completed | Completed
58 | SANDFORD GROVE ROAD | Nether Edge | 1 | Design Solution Outstanding | No joint inspections to date. Carriageway completed above speed cushion towards Archbald Road. Below the speed cushion surfacing remains outstanding, Various defects remain to be resolved prior to any planned surfacing works. Build out to be constructed for the tree outside 82. Various other engineering solutions required on the street for trees not initially in scope of CIP | B | Requires design solutions & build | 23/24
59 | SHELDON ROAD | Nether Edge | 7 | Design Solution Outstanding | Site investigation required to consider options available due to the severity of ramping and obstruction along the footway. October 2021 Update: Designed solution still to follow from Amey | B | Requires design solutions & build | 24/25
60 | SILVER HILL ROAD | Ecclesall | 5 | Design Solution Outstanding | Carriageway and footway reconstruction outstanding. Footway requires tree pit constructing, displaced kerbs and rooting into the carriageway present. Outside 17: hand excavation in proximity to the tree to reinstate the kerb line potentially using edging if the presence of roots prevents use of a full kerb being reinstated, accepting relaxation of current standards. Public consultation to follow for the following engineering works: Outside 18 & 29: further excavation of the trees is required to determine the extent of the rooting into the carriageway including depth. Buildouts will be required to provide a permanent solution. Aim to minimise the width of the buildout to allow surfacing works to be progressed without damaging the roots. Estimate to be no greater than 500mm from the existing kerb. This is a change to the highway network. Junction with Mylnhurst Road: based upon experience to date, the aim is to reinstate the kerb line using an edging or thin kerb. These recommendations ensure the trees are retained on a permanent basis, through the introduction of several changes to the highway network, whilst mindful of minimising residential access through design. | B | Requires design solutions & build | 23/24
61 | SPRING HILL ROAD | Broomhill | 9 | Design Solution Outstanding | Carriageway reconstruction outstanding, with footways only partially resurfaced, various defects associate with the kerb line, potential rooting into the carriageway and footway ramping remains. The Council will now progress a resident consultation on numerous proposed engineering changes to the highway network here. The introduction of the build outs is essential to enable the trees to be retained and maintain a footway for users. However following site investigations into the extent of the root intrusion in the carriageway, it may be acceptable to leave the kerbs out, accepting the continued relaxation of current standards. The footway as highlighted above requires a reconstruction, removing historic patches and to reprofile, using a permeable surface solution to minimise future maintenance. | B | Requires design solutions & build | 23/24
62 | SPRINGVALE ROAD | Crookes | 2 | Closed | Two trees remaining to action, o/s church, no kerb defects, limited to footways which are raised due to the presence of roots, with the exception of the 2 trees the remaining footways have been completed. Hand dig, construct tree pits and remedy footway. Carriageway to be resurfaced 2021 with footways actioned at the same time. No joint inspections undertaken. | A | Completed | Completed
63 | ST RONAN'S ROAD | Nether Edge | 2 | Design Solution Outstanding | Majority of the issues are footway only with the kerb defects generally addressed, though a number of kerbs to be trimmed, marked up on site. Tree pits within footways to be extended to facilitate the footway works to be concluded & surfaced. | C | Requires design solutions & build | 23/24
64 | STANLEY ROAD | Gleadless Valley | 5 | Closed | Through the joint inspections kerbs were reinstated, raised footway (ramping) addressed and tree pits installed. Carriageways have been completed, footways now planned for 2021 | A | Completed | Completed
65 | STEADE ROAD | Nether Edge | 3 | Design Solution Outstanding | Numerous kerb line and footway defects to be addressed, to facilitate the outstanding carriageway reconstruction. To minimise the impact on the street scene and provision of on-street parking, a combination of ongoing compromise to current standards will be required in relation to missing kerbs, accepting where there is no root intrusion to impede resurfacing of the carriageway. Following further investigation where build outs are required, they are similar to Rundle Road where they are minimised in length and width. | B | Requires design solutions & build | 23/24
66 | STRUAN ROAD | Nether Edge | 1 | Closed | Remedial works undertaken, through joint inspections - Excavation of roots with airspade took place, roots were pruned as required. Kerbs were cut on site and re-laid on a bed of concrete over a tree root protected with semi-permeable membrane. An enlarged tree pit was formed with wood battens. Subsequently, the pavement was resurfaced, with an adequate walkway between the tree pit and boundary wall. Tree pit filled with bark chippings. Surfacing works concluded | A | Completed | Completed
67 | TAY STREET | Walkley | 1 | Closed | Remedial works undertaken through joint inspections, extended new tree pit was shaped to accommodate a long uphill root within the space available. The kerbstone was halved and replaced to the front of the tree. Asphalt surface was levelled to the wall. Flexipave will be used to complete the work outstanding. | A | Completed | Completed
68 | THE OVAL | Firth Park | 2 | Closed | Remedial works undertaken, works concluded, No joint investigation undertaken. The work had already been carried out before the joint inspections were initiated. | A | Completed | Completed
69 | THOMPSON ROAD | Broomhill | 4 | Design Solution Outstanding | No joint Inspections undertaken, both Carriageway and Footway reconstruction remains outstanding from Ecclesall Road to 10m beyond the park entrance. Replacement status cancelled . Tree close to Botanics Entrance - Amey propose to reposition the gully and drainage system and change the radius of the kerbline, effectively losing around 2-3 metres of space in the final parking bay on the street Several missing kerbs along the street, so hand digging and reinstatement where possible will be undertaken Proposal is to strip off the asphalt surfacings and expose the historical cobbles which may allow additional works to be done to the channel and kerbline Use of flexible, permeable paving materials may be required due to the extent of root damage in some instances on the footway | C | Requires design solutions & build | 23/24
70 | THORNSETT ROAD | Nether Edge | 10 | Design Solution Outstanding | Site investigation to be concluded Mid May 2021, to inform available options with surfacing planned for carriageway and footways in 2021 | B | Requires design solutions & build | 23/24
71 | THORPE HOUSE AVENUE | Graves Park | 1 | Closed | Remedial works undertaken, and concluded, no joint inspection as works already concluded | A | Completed | Completed
72 | UPPER ALBERT ROAD | Gleadless Valley | 3 | Design Solution Outstanding | Tricky root in the kerb line at the Tree by No3. Possibility of an extension to a nearby build out / traffic calming measures as design. Temporary repair prior to further investigation in place undertaken as part of the joint inspections with STAG, surfacing to progress 2021 | B | Footways complete, requires design solutions & build for c/way. | 23/24
73 | VERNON ROAD | Dore & Totley | 1 | Closed | Design solution for Carriageway and Footway and impact on neighbouring property concluded, No joint Inspection necessary and works completed, Carriageway resurfacing planned 2021 | A | Completed | Completed
74 | WAYLAND ROAD | Nether Edge | 2 | Closed | Remedial works undertaken, resurfacing works concluded, during joint inspections kerbs reset and historic build up of asphalt creating ramping removed, no roots evident in the raised footway defects tree pits created. | A | Completed | Completed
75 | WESTERN ROAD | Crookes | 23 | Closed | Design solution proposed, implement and concluded in 2020 / early 2021 | A | Completed | Completed
76 | WHIRLOWDALE CRESCENT | Ecclesall | 2 | Closed | Remedial works undertaken, installing kerbs and edges that meet the relaxed specification with increased monitoring and maintenance. No joint investigation. | A | Completed | Completed
77 | WOODSTOCK ROAD | Nether Edge | 8 | Design Solution Outstanding | The Council will now progress to a resident consultation to seek views over the extents of engineering works required to retain the trees and assosciated loss of parking for this street as well as potential replacement of 3 trees | B | Requires design solutions & build | 24/25
78 | WOSTENHOLM ROAD | Nether Edge | 1 | Closed | Carriageway has been resurfaced, the footway defects addressed and tree pit constructed, root present in Kerb line, however kerbs in situ and the carriageway resurfacing wasn't impeded. | A | Completed | Completed
| Total |  | 306
Key
| Completed | 48 | A
| Consultation/Potential Consultation Sites | 18 | B
| Design Outstanding Consultation Unlikely | 8 | C
| Delivery Programmed | 4 | D
| Total | 78