## 170517_Publish
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
RUNDLE ROAD | o/s 40-42 | Tilia x europea | Growing into c/w - kerbs absent | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | adj hotel, 2nd tree from top/Kenwood Rd | Tilia x europea | C/W incursion at <5.2m, growing within c/w, kerb absent | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 1 (3rd tree from junc Kenwood rd.), alongside driveway for Kenwood Knoll | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. Thinner Kerb | N/A | Roots under kerb line lifting channel: Roots travelling to wall where damage previously repaired: Wall now showing further minor damage. Thinner kerb will not address these issues. Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 58 | Tilia x europea | Growing in c/w, c/w uplifted, stem incursion in c/w, unable to raise profile due to gully, preventing edge planing | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 9 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. Ramping | N/A | Roots lifting channel: Kerb pushed into channel line: roots tracing towards wall. Ramping will not address all issues adequately. Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 11, just before junction with Kenbourne Rd | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 56 | Tilia x europea | Growing in c/w, c/w uplifted, stem incursion in c/w, preventing edge planing | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 30 | Tilia x europea | Kerbs displaced and rooting between kerbs, potential root damage to 3rd party wall | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 19 | Tilia x europea | TR: Felling, damage to network | Reinvestigate. Remove Kerb, Root Pruning | N/A | Pushing into kerb line and damaging channel. Roots in footway and carriageway ramp would be too severe. A 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement. Severance or pruning of roots immediately adjacent to the main stem is not only extremely poor arboricultural practice but would also render this tree structurally unsound in a high wind event, so this is also impossible to implement. Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 50 | Tilia x europea | Rooting into c/w - kerbstone absent, rooting above tarmac in f/w, too close to stem to viably root prune | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 24 | Tilia x europea | 2no kerbs and radius absent, cannot adequately install without tree removal | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 14 | Tilia x europea | Extensive kerb displacement and rooting between multiple kerbs, cannot repair to specification at all without significant root damage | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 48 | Tilia x europea | extensive kerb displacement - cannot reset/achieve alignment at all without tree removal | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 12 | Tilia x europea | Growing in c/w, c/w uplifted, unable to raise profile due to gully, preventing edge planing | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 72 | Tilia x europea | Rooting between kerbs into c/w, unable to repair to standard without root damage, and c/w incursion | Reinvestigate. Root Pruning, Larger Tree Pit | N/A | Roots lifting and damaging channel and pushing into carriageway. Roots in footway and carriageway ramp would be too severe. A 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement. Severance or pruning of roots immediately adjacent to the main stem is not only extremely poor arboricultural practice but would also render this tree structurally unsound in a high wind event, so this is also impossible to implement. Larger Tree pit will also not address all of issues present. Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 70 | Tilia x europea | Rooting over kerbs into c/w, unable to work round at all without root damage | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
RUNDLE ROAD | o/s 44 | Tilia x europea | Growing into c/w - c/w uplifted and cracked | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
SACKVILLE ROAD | O/S 48 | Sorbus aucuparia | Structural Integrity | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
SACKVILLE ROAD | O/S 38 | Platanus x hispanica | TR: Felling - Kerb Displaced by roots. Unable to reset | Engineering Solutions. | N/A | Kerb displaced. Roots beneath wall causing damage: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
SACKVILLE ROAD | O/S 31 | Tilia x europea | TR: Felling - Kerb displaced by roots. Unable to reset/repair | Engineering Solutions. | N/A | Kerb displaced. Severe kerb displacement by roots in channel partly blocking drive and reduced footway: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
SACKVILLE ROAD | O/S 58 | Tilia x europea | TR: Felling - Roots grown under and displaced kerb. Unable to repair | Engineering Solutions. | N/A | Kerb displaced. Severe root damage kerb displaced any ramping would cause backfall to property: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
STEADE ROAD | o/s 29 | Tilia x europea | TR: Felling, (note bird box on tree) | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
STEADE ROAD | o/s 49 | Acer pseudoplatanus | No kerb, buttress root growing in c/w - no option but to remove tree or leave section out | Engineering Solutions. Remove Kerb | N/A | Roots in carriageway causing damage unable to place kerb or leave kerb out: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
STEADE ROAD | o/s 21 | Tilia x europea | No kerb, buttress root growing in c/w - no option but to remove tree or leave section out | Engineering Solutions. Remove Kerb | N/A | Roots in carriageway causing damage unable to place kerb or leave kerb out: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
UPPER ALBERT ROAD | o/s 31 | Tilia x europea | F/W narrowed/obstructed | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
UPPER ALBERT ROAD | o/s 33 | Tilia x europea | F/W narrowed/obstructed | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
UPPER ALBERT ROAD | o/s 29 | Tilia x europea | F/W narrowed/obstructed | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
UPPER ALBERT ROAD | o/s 6 | Tilia x europea | TR: Felling, network damage | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
UPPER ALBERT ROAD | opp 7 | Tilia x europea | TR: Felling, network damage | Engineering Solutions. Remove Kerb, Larger Tree Pit | N/A | Roots tracing to private wall and overgrown kerb pushed out of line, solutions will not address all issues present: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
UPPER ALBERT ROAD | O/S 3 | Aesculus hippocastanum | Kerb absent, f/w mounded, rooting in c/w | Engineering Solutions. Remove Kerb, Larger Tree Pit | N/A | Footway narrowing : Roots tracing to private wall damage evident: verge to drive lifting at rear of footway: recently repaired footway ramp and channel regulating: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
VAINOR ROAD | o/s 25 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. Remove Kerb | N/A | Roots in channel already severe ramping: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
VAINOR ROAD | o/s 40 | Platanus x hispanica | TR: Felling, damage to network | Consider exceptional engineering solution to retain tree. Very fine prominent tree. Kerb displaced. Rooting in carriageway. | N/A | Severe damage to footway / carriageway and gate posts If ramping provided it will give backfall to property, which is not acceptable: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
VAINOR ROAD | o/s 39 | Fraxinus excelsior | TR: Felling - Damage to network | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
VAINOR ROAD | Side of 53 marlcliffe road. | Platanus x hispanica | TR: Felling, damage to network | Tree already removed N/A | N/A | Tree already removed. | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
VAINOR ROAD | o/s 10 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. Remove Kerb, Larger Tree Pit | N/A | Kerb pushed into channel line: roots tracing towards wall although no damage recorded, solutions will not address all issues present: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
VAINOR ROAD | o/s 47 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | O/S 22 | Fraxinus excelsior | TR: Felling - Damage to surrounding footway and kerbs by buttress. Too large for verge to contain | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | O/S 44 | Fraxinus excelsior | Roots causing damage to customers drive at 44. (TR: Felling-) | Confirm whether damaged being caused. 3rd party damage – not visible. | N/A | Roots tracing to drive and buttress protruding into vehicular crossing and is liable to be stuck: Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | O/S 60 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress. Unable to reset | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | OPP 52 | Fraxinus excelsior | TR: Felling - Footway ramped by shallow surface roots | Engineering Solutions. Ramping | N/A | Roots tracing into garden lifting verge: Buttress in carriageway overgrown kerb and roots protruding into and above footway at verge. Ramping will not address all issues present. Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | O/S 33 | Fraxinus excelsior | TR: Felling - Moderate dieback. Less than 5 years safe useful life expectancy | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | OPP 6 | Fraxinus excelsior | TR: Felling - Kerb displaced by roots. Unable to reset. | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | O/S 1 | Fraxinus excelsior | TR: Felling - Basal Decay. Footway damaged by shallow roots. | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WARMINSTER CRESCENT | O/S 28 | Fraxinus excelsior | TR: Felling - Ganoderma decay fungi in west buttress. | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WOODBANK CRESCENT | o/s 11 | Prunus avium | Basal heartwood decay, Ganoderma sp. identified in past | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WOODBANK CRESCENT | o/s 9 | Prunus avium | kerb damaged, buttress root pushing immediately behind | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
WOODBANK CRESCENT | o/s 1 | Prunus avium | decayed topping points into stem at crown break, tightly adpressed scaffolds also, poor structural condition | Remove and replace tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
BURLINGTON ROAD | O/S 18 | Crataegus sp | Stem base decayed | We advise that the Council should take steps to prevent this happening again. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
BURLINGTON ROAD | O/S 21 | Prunus sp | F/W mounded and uplifted and stem bark necrosis | We advise that given this level of damage the Council would be justified in removing and replacing this tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
BURLINGTON ROAD | O/S 33 | Prunus serrula | F/W mounded and stem base wounded | We therefore advise that the Council could reconsider its plans for these four trees. We recognise that in considering this advice the Council will take into account the low response rate to the household survey, with only two of 40 households objecting to the Council’s plans. | N/A | Roots into garden area causing uplift: Recommend Replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
BURLINGTON ROAD | O/S 42 | Prunus serrula | F/W uplifted and cracked | We therefore advise that the Council could reconsider its plans for these four trees. We recognise that in considering this advice the Council will take into account the low response rate to the household survey, with only two of 40 households objecting to the Council’s plans. | N/A | Roots into garden area causing uplift: Recommend Replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
BURLINGTON ROAD | O/S 40 | Prunus serrula | F/W uplifted and cracked | We have already written to you with advice about the tree outside number 40. Summary of letter cited: We therefore advise that the Council may wish to take immediate action to resolve this problem, either by a temporary measure to make good the pavement, or by removing the tree, pending replacement, and making good the pavement. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
BURLINGTON ROAD | opp 50 | Prunus sp | Kerbs missing, unable to adequately repair without tree damage/removal | We therefore advise that the Council could reconsider its plans for these four trees. We recognise that in considering this advice the Council will take into account the low response rate to the household survey, with only two of 40 households objecting to the Council’s plans. | N/A | Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement. Recommend replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 238 | Platanus x hispanica | Kerbs displaced, f/w mounded, stem within c/w at <5.2m | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree outside number 238 is leaning towards Psalter Lane, is showing signs of slow failure, is disrupting the pavement and damaging the neighbouring boundary wall. We advise that this tree should be removed as a matter of priority and replaced. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 155 | Platanus x hispanica | Extensive kerb displacement - unable to realign without significant root damage, lateral rooting through tarmac in f/w also, will be damaged upon planing off | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 155, 177, 181, 188 and outside Hunter Court (opposite 149) are causing significant damage to the pavement and kerb. We do not believe there to be engineering solutions which could resolve these problems. We advise that these trees should be removed and replaced. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 177 | Tilia x europea | Kerbstone missing, f/w damaged, cannot repair without unacceptable root damage | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 155, 177, 181, 188 and outside Hunter Court (opposite 149) are causing significant damage to the pavement and kerb. We do not believe there to be engineering solutions which could resolve these problems. We advise that these trees should be removed and replaced. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 181 | Tilia x europea | Kerbstone missing, f/w damaged, cannot repair without unacceptable root damage | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 155, 177, 181, 188 and outside Hunter Court (opposite 149) are causing significant damage to the pavement and kerb. We do not believe there to be engineering solutions which could resolve these problems. We advise that these trees should be removed and replaced. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 188 | Acer pseudoplatanus | Rooting between kerbs into c/w, f/w mounding rendering f/w effectively unusable | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 155, 177, 181, 188 and outside Hunter Court (opposite 149) are causing significant damage to the pavement and kerb. We do not believe there to be engineering solutions which could resolve these problems. We advise that these trees should be removed and replaced. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s hunter court, (opp 149) | Acer pseudoplatanus | Kerb line displaced - unable to realign without significant root damage | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The trees outside numbers 155, 177, 181, 188 and outside Hunter Court (opposite 149) are causing significant damage to the pavement and kerb. We do not believe there to be engineering solutions which could resolve these problems. We advise that these trees should be removed and replaced. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 167 | Tilia x europea | Kerbs displaced, no way at all to repair with tree insitu | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree outside numbers 167 is causing less damage to the pavement and kerb. However, it appears to be causing damage to the neighbouring boundary wall and possibly property. We advise that this justifies the removal and replacement of this tree. | N/A | Continue with tree replacement as planned. | ITP, SCC and Amey in Agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 145 | Tilia x europea | Extensive kerb displacement - unable to realign without significant root damage | The trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree outside 145 does not appear to be causing any damage that would require any engineering work. We advise that there does not appear to be any need to remove and replace this tree. | N/A | Roots tracing towards wall at rear showing slight damage. Unable to mound footway due to crossfalls and ponding and freezing water: Receommend Replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
HUNTER HOUSE ROAD | o/s 176 | Tilia x europea | Kerbs absent, unable to install without root damage, rooting above tarmac level in f/w also | The tree outside number 176 is causing less damage to the pavement and kerb. The tree could, we believe, be retained using engineering options 1, 3, 7 and 12 (thin kerbs, ramping and reprofiling the footway, tree pits, root pruning), leading to the pavement, kerb and carriageway being satisfactory for all road users. We advise the Council to consider this. | N/A | Footway already made into carriageway causing slight obstruction to kerbline. This needs removing and tree replacing as roots are high and will be struck: Recommend Replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
STOCKARTH LANE | O/s 1a | Quercus petraea | Growing within c/w, obstructive | The tree, a sessile oak, is in good condition and has good life expectancy. We advise that there is no arboricultural need to remove this tree. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of this tree. The tree is located at the edge of the carriageway on the upside of the driveway to number 1a. There is no pavement. The tree therefore poses some risk of vehicle impact, and there is evidence of previous impact. However, we do not believe this justifies the removal and replacement of this tree. We believe that the installation of a simple hazard post (e.g. a zebraflex post), road markings or other appropriate hazard warnings would be sufficient. We therefore advise the Council to consider this. | N/A | Tree is protruding into carriageway which could cause accident. Severe damage to wall and brickwork: Recommend Replacement | ITP Advice considered and investigated, found to be not viable. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17