## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
THORPE HOUSE AVENUE | o/s 32 | Acer platanoides | TR: Felling - Vehicle crossing surface damaged by shallow roots. | Engineering Solutions. | Filling Pavement |  | Damage to kerb frontage and crossing area. Part obstructing crossing. Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 80 | Acer platanoides | TR: Felling - Kerb line bowed out by roots. Unable to realign. | Retain Tree. | None |  | Ramp area of footway leave kerb: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 116/114 | Acer platanoides | TR: Felling - Kerb displaced by buttress roots. Unable to reset. | Engineering Solutions. | Thinner Kerb |  | Large root visible in middle of vehicle crossing: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 118 | Acer platanoides | TR: Felling - Kerb displaced by root. unable to reset. | Engineering Solutions. | Thinner Kerb |  | Adjust kerb and ramp footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 77 | Acer platanoides | TR: Felling - Kerb displaced by buttress roots. Unable to reset. | Retain Tree. | None |  | Ramp footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 75 | Acer platanoides | TR: Felling - Footway damaged by shallow roots. Rooting into carriageway | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 47 | Acer platanoides | TR: Felling - Footway damaged by shallow roots | Engineering Solutions. | Filling Pavement |  | 4 roots are growing through kerb into cway: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 37 | Acer platanoides | TR: Felling - Footway damaged by shallow roots | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 13 | Acer platanoides | TR: Felling - Cannot reinstall full profile kerb due to buttress. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
THORPE HOUSE AVENUE | o/s 22 | Acer platanoides | TR: Felling - Vehicle crossing ramped by shallow roots | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ALDAM WAY | CAR PARK, between 11-15 | Alnus glutinosa | Fell both stems (TR: Felling-) | Retain Tree. | None | ITI | Roots tracing under footway would incur severe ramp. Tree (half leaning) over footway. No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LATHKILL ROAD | o/s 33-35 | Prunus sp | TR: Felling- damaging network | Remove and replace tree. | Reconsider replacement location owing to telegraph pole. |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LATHKILL ROAD | o/s 34 | Prunus sp | TR: Felling- damaging network and structures | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LATHKILL ROAD | o/s 26-28 | Prunus sp | TR: Felling- damaging network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LATHKILL ROAD | o/ 21 | Malus sp | TR: Felling- damaging network | Retain Tree. | None |  | Surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
LATHKILL ROAD | opp 32 (outside 46 Masefield Rd) | Prunus sp | TR: Felling: Structural Integrity | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
SMELTER WOOD ROAD | opp 9 to 11 | Platanus x hispanica | TR: Felling: Structural Integrity | Retain Tree. | None | ITI | Surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
The Grove | O/S 26 | Prunus Kanzan | Kerbs displaced/pushed by roots directly behind | Engineering Solutions. | None |  | Trim kerb and ramp over footway. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
The Grove | O/S 60 | Fraxinus excelsior | Growing entirely within c/w, impossible to retain/work round | Retain Tree. | None |  | Temporarily Retain Tree and monitor. | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
The Grove | O/S 2 | Prunus Kanzan | Extensive f/w uplift, f/w cracking | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
The Grove | O/S 1 | Prunus Kanzan | F/W mounded, recently patched, cracking again | Engineering Solutions. | None |  | Roots showing in footway and into garden. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
The Grove | O/S 6 | Prunus Kanzan | Has Pholiota | Reinvestigate. | None | ITI | Tree with significant structural and physiological flaws and/or extremely stressed: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
The Grove | O/S 3 | Prunus Kanzan | F/W mounded, recently patched, cracking again | Engineering Solutions. | None |  | Work already done to footway. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
The Grove | O/S 7 | Prunus Kanzan | F/W mounded, recently patched, cracking again | Engineering Solutions. | None |  | Roots showing in footway and through to wall. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 71 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Half width or dropped kerb. |  | Existing concrete in place of kerb; no evidence of root damage: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 67 | Acer pseudoplatanus | TR: Felling, damage to network | Engineering Solutions. | Half width or dropped kerb. |  | Roots slight in kerb line but okay. Leave out kerb: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 48 | Acer pseudoplatanus | TR: Felling, structurally poor specimen | Retain Tree. | None | ITI | Kerb displaced and footway already creating backfall. Roots tracing under footway and channel. No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 62 | Acer pseudoplatanus | TR: Felling, structurally poor specimen | Retain Tree. | None | ITI | Kerb can be cut by Stihl saw: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 79 | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 63 | Tilia x europea | TR: Felling, damage to network and senescent | Retain Tree. | None | ITI | Kerb can be cut by Stihl saw: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 66 | Tilia x europea | TR: Felling, structurally poor specimen | Retain Tree. | None | ITI | Kerb can be cut by Stihl saw: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 59 | Fraxinus excelsior | TR: Felling, damage to network | Retain Tree. | None | ITI | Roots in carriageway. Existing thin kerb displaced: No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 56 | Fraxinus excelsior | Historically topped, weakly attached phototropic regrowth, poor structural condition, extensive kerb and f/w damage also | Retain Tree. | None | ITI | Severe damage to footway, thin kerb displaced. Roots tracing along footway and into carriageway. No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 52 | Acer pseudoplatanus | TR: Felling, structurally poor specimen | Retain Tree. | None | ITI | Kerb displaced and footway already creating backfall. Roots tracing under footway and channel. No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 40 | Fraxinus excelsior | TR: Felling, structurally poor specimen | Retain Tree. | None | ITI | Kerb/ concrete fillet displaced into c/way. Footway ramped and cracked with roots tracing into channel and toward GPO box. Also backfall in footway. No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 30 | Acer pseudoplatanus | TR: Felling, structurally poor specimen | Retain Tree. | None | ITI | Roots under pushed out kerb and in carriageway. Severe ramp in and edging displaced. No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | o/s 11 | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
WOODSTOCK ROAD | adj church | Acer pseudoplatanus | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
OXFORD STREET | by bank | Platanus x hispanica | TR: Felling - Kerb displaced by buttress, unable to reset | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
OXFORD STREET | o/s 526 | Acer pseudoplatanus | TR: Felling - Kerb displaced by buttress. Unable to reset | Engineering Solutions. | Thinner Kerb, Remove Kerb |  | Trim the kerb and provide slight ramp to footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
OXFORD STREET | opp 538 | Acer pseudoplatanus | TR: Felling - Kerb displaced by root, unable to reset | Engineering Solutions. | Thinner Kerb, Remove Kerb |  | Half kerb and Ramp: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
OXFORD STREET | opp labs | Acer pseudoplatanus | TR: Felling - Kerb displaced by buttress. Unable to reset | Engineering Solutions. | Thinner Kerb, Remove Kerb |  | Half kerb and Ramp: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
OXFORD STREET | by bank | Platanus x hispanica | TR: Felling - Kerb displaced by buttress, unable to reset | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
OXFORD STREET | by bank | Platanus x hispanica | TR: Felling - Kerb displaced by buttress unable to reset | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
OXFORD STREET | by school | Platanus x hispanica | TR: Felling - Kerb displaced by buttress | Engineering Solutions. | Thinner Kerb, Remove Kerb |  | This is the last tree at the end of the school wall opp Ponderosa Entrance. Thin kerbs already displaced and roots lifting cway: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
OXFORD STREET | last tree on right if facing Albion St | Acer pseudoplatanus | TR: Felling - Kerb displaced by buttress unable to reset | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | opp 196 | Aesculus sp | TR: Felling - Large mounding at the tree base - suspect shallow rooting in the footway. | Remove and replace tree. | Reconsider location for replacement tree away from bus stop. |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | opp 68 | Tilia sp | TR: Felling: Decay | Retain Tree. | None | ITI | Roots causing damage to footway and into gardens of the rear property: No engineering solutions proposed by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | o/s 146 | Acer platanoides | TR: Felling: Structural Integrity | Retain Tree. | None | ITI | Due to deteriorating condition removed as unsafe: Replace as Planned | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | o/s 149 | Platanus x hispanica | TR: Felling weak union at crown break - structural integrity | Retain Tree. | None | ITI | Surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | o/s 137 | Tilia sp | TR: Felling: Decay | Retain Tree. | None | ITI | Surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | o/s 133 | Tilia sp | TR: Felling: Decay | Retain Tree. | None | ITI | Surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | o/s 118 | Tilia sp | TR: Felling: Decay | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
RIDGEWAY ROAD | opp 60 | Sorbus intermedia | TR: Felling: Decay | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 90 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 92-94, between the two | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 76 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 9, opposite 12 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Dropped kerb. |  | Missing Kerb, roots in crossing partially blocking drive. Footway already ramped due to roots. Dropped kerb not a solution to roots in crossing: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 99-101, next to driveway | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Taper radius kerb. |  | Kerb missing but roots okay as no damage occurring: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 102 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Half width or dropped kerb. |  | Roots in footway, cracks showing in third party wall. Half width kerb would not be possible due to roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 29 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Remove deadwood overhanging carriageway. Root prune (which will not compromise tree) and half width kerb. |  | Large Root Buttress in channel and carriageway. Half width kerb not possible. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 72 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 28 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Dropped kerb or leave as is. |  | Kerb missing but okay, no damage: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 74 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 22 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 88 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 6b and 6c | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 97 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Dropped kerb or leave as is. |  | Kerb missing but okay, no damage: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 78 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 96 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 82 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 80-82 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 14-16 (toward 14) | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Root prune. Dropped or half width kerb. Redo tree pit. |  | Root Buttress in channel and carriageway and to property. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
MONTGOMERY ROAD | o/s 13-15 | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Dropped kerb on radius. |  | Footway okay kerb slightly leaning but okay: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
BLAYTON ROAD | o/s 23 | Prunus sp | TR: Felling - Footway damaged by shallow roots | Engineering Solutions. | Build out requires comprehensive repairs. Consider scope to retain trees in repaired build out. Consider scope to plant additional tree in already vacant tree pit. |  | Severe damage to footway and build out with roots tracing to properties: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
BLAYTON ROAD | o/s 21-23 | Prunus sp | TR: Felling - Footway damaged by shallow roots | Engineering Solutions. | Build out requires comprehensive repairs. Consider scope to retain trees in repaired build out. Consider scope to plant additional tree in already vacant tree pit. |  | Severe damage to footway and build out with roots tracing to properties: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
CRABTREE DRIVE | o/s 20 | Malus sylvestris | TR: Felling - buttress root enveloping edging at rear of pit. | Engineering Solutions. | Larger Tree Pit |  | Extend tree pit slightly and ramp over: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
CRABTREE DRIVE | o/s 14 | Pyrus Chanticleer | TR: Felling - kerb displacement, no scope to install full profile kerb | Engineering Solutions. | Thinner Kerb |  | Slight raising of carriageway. Roots in footway slight. Half kerb possible solution dependent on roots. Trim kerb if this is not possible and ramp footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
EAST BANK ROAD | O/S 648 | Fraxinus excelsior | Root damage to footway. (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | O/S 186 | Acer platanoides | Surface damage -suspect shallow rooting. (TR: Felling-) | Engineering Solutions. | Root prune. Repair footway. |  | Roots pushing up large area of footway, previous repaired part of footway. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | OPP 204 | Populus sp | Surface root in footway - unable to root prune (TR: Felling-) | Engineering Solutions. | Repair footway. |  | Major cracks and footway damage pushing up previously repaired section. Repair to footway not feasible due to cracking: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | OPP 214 | Platanus x hispanica | Shallow rooting in the footway with evidence of previous root severance. (TR: Felling-) | Engineering Solutions. | Repair footway. |  | Major cracks and footway damage pushing up previously repaired section: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | O/S 654 | Fraxinus excelsior | Dead/dying canopy over 50% dead. (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | O/S 644 | Fraxinus excelsior | Stem decay (reoccurring root damage plus high potential of previous root severance by highway engineers ) (TR: Felling-) | Retain Tree. | None | ITI | Roots tracing across wide footway to property. ITI verifies ITP findings: Temporarily Retain Tree and Monitor | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
EAST BANK ROAD | O/S 459 | Sorbus intermedia | Ganoderma infection (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | OPP 206-8 | Populus sp | Crown 50% dead (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
EAST BANK ROAD | OPP 208 | Populus sp | High potential for limb failure -previous failure evident. (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 62 | Fraxinus excelsior | TR: Felling - Kerb/edgings displaced. Tree has grown to limit of available space. | Engineering Solutions. | Reset Kerb |  | Roots causing slight damage to crossings: Extending vehicular crossing would assist and ramp over: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 37/35 | Fraxinus excelsior | TR: Felling - Kerbs displaced by buttress, unable to reset. Footway ramped by shallow roots | Engineering Solutions. | Thinner Kerb, Ramping |  | Roots tracing to property with kerb pushed into carriageway. Verge also pushed up with severe roots tracing to third party. Unable to re-set kerb or utilise half kerb due to roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 72/74 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress. Footway ramped by shallow roots. | Engineering Solutions. | Reset Kerb |  | Roots tracing to kerb and gully. Access recently repaired. Roots under wall and in channel. Verge recently repaired now pushed up. Narrowed footway. Roots under kerb and verge, unable to reset: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 45 | Fraxinus excelsior | TR: Felling - Kerbs displaced by buttress. Unable to reset | Engineering Solutions. | Remove Kerb |  | Kerb bowing into channel however no damage to carriageway or footway evident footway. Leave kerb for now and surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S52/54 | Fraxinus excelsior | TR: Felling - Kerb and edgings displaced by buttress. Unable to reset | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 36/38 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress. Unable to reset. Footway damaged by shallow roots | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 45/43 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress. Unable to reset. | Engineering Solutions. | Thinner Kerb, Remove Kerb |  | Kerb bowing into channel and verge edging slightly displaced with no significant damage to footway. Leave kerb for now and surface footway: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 8 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress. Unable to reset. Footway ramped by shallow roots. | Engineering Solutions. | Reset Kerb |  | : Roots tracing under wall causing damage to wall. Resetting kerb or verge not possible due to roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 20 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress. Unable to reset | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 4 | Fraxinus excelsior | TR: Felling - Kerbs displaced by buttress. Unable to reset. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 2 | Acer pseudoplatanus | F?W obstructed and damaged, unable to repair footway without extensive root damage. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
LEES HALL AVENUE | O/S 88/90 | Fraxinus excelsior | TR: Felling - Kerb displaced by buttress, Unable to reset | Retain Tree. | None |  | Roots tracing to wall recently repaired. Lifting verge edging in adjoining garden and footway lifted: Ramping would only hide problem. Kerb overgrown by roots. Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 377 Party Shop | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Redo kerb and footway. |  | Severe roots in carriageway. Existing thin kerb displaced. Roots tracing to forecourt causing distortion. Unable to carry out further ramping due to backfall and roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/S 397, opposite 388, o/s Starbucks | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Half width kerb. Redo tree pit. |  | Severe roots in carriageway lifting. Existing thin kerb displaced. Roots tracing to forecourt causing distortion unable to carry out further ramping due to backfall and roots under carriageway makes half kerb not possible: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 565, outside Sainsbury Local | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 521-523, O/S Mud Crab Cafe | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Half width kerb. |  | No evidence of damage in carriageway. Slight ramping of footway. Adjust and trim kerb and extend pit: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | Opp Botanical Road, o/s 605 Church Hall | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Half width kerb. |  | Roots evident in carriageway channel. Existing kerb pushed out. Roots tracing across footway causing distortion and backfall to church. Half width kerb not an option as it would be situated on roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s Vodaphone shop 399-401, opposite 396, | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Excavate and investigate scope to prune roots, which will not compromise tree. |  | Severe roots in carriageway lifting. Existing thin kerb displaced. Roots tracing to forecourt lifting setts unable to carry out further ramping due to backfall and roots under carriageway makes half kerb not an option. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 365, o/s Flora flower shop | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Remove asphalt repair to investigate scope for dropped or half width kerb. |  | Roots in carriageway severe, also to forecourt with ponding evident. Ramping would cause further backfall and half or dropped kerb not possible due to large roots in c/way. Also roots tracing to Post Box: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 297-299, White Stuff | Acer platanoides | TR: Felling, damage to network | Engineering Solutions. | Dropped or half width kerb. |  | The kerb is slightly pushed out. Adjustments to existing kerb and trimming rather than half or dropped kerb: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | Os 367, o/s Hardys Gunsmiths | Acer pseudoplatanus | TR: Felling, Poor physiological condition | Retain Tree. | None | ITI | The tree has very poor foliage density and low vigour. The tree has a large volume of dead wood. The tree is clearly in decline and there is little prospect of recovery: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 393, FABLE charity shop | Acer pseudoplatanus | TR: Felling, Poor physiological condition | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 319, o/s Graze Inn | Acer pseudoplatanus | TR: Felling, Poor physiological condition | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | Os 397, lime o/s Starbucks | Tilia x europea | TR: Felling, Poor physiological condition | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12
ECCLESALL ROAD | O/s 629/Leason financial Advisors | Acer pseudoplatanus | TR: Felling, dying/poor physiological condition | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-07-12