## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
SPRINGVALE ROAD* | O/S CHURCH nearest to cobden view jct | Acer pseudoplatanus | TR: Felling - Extensive ramping of footway by surface roots. Kerb Displaced unable to reset | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
SPRINGVALE ROAD* | O/S CHURCH | Acer pseudoplatanus | TR: Felling - Obstructing carriageway below 5.2m | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BOWER ROAD | Opp 83 Bower Rd. At jct spring hill road. | Acer pseudoplatanus | Footway excessively ramped by surface roots. (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BRIGHTON TERRACE ROAD | O/S 64 | Sorbus aucuparia | TR: Felling - Footway damaged by shallow surface root. | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BRIGHTON TERRACE ROAD | O/S 19 | Prunus Kanzan | TR: Felling - Footway damaged by shallow surface roots | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
AGDEN ROAD | O/S 3-5 | Acer pseudoplatanus | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
AGDEN ROAD | O/S 34, (last tree on road before Kenwood Pk Rd) | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. Thinner Kerbs, Tree Pit | N/A | Kerb displaced. Unable to provide half width kerb as roots are in c/way channel. Larger pit will not impact kerbing issue. Recommend replacement. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
AGDEN ROAD | At side of 48 Kenwood Park Road, on THORNSETT RD though, 2nd tree from junction | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
ALBANY ROAD | SIDE OF 53 WOSTENHOLM RD, top of Albany road by junct with Wostenholm Rd | Tilia x europea | F/W mounded/uplifted, unable to achieve crossfalls by surfacing over | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
ALBANY ROAD | O/S 56, at top Albany Rd at junc with Wostenholm | Tilia x europea | Extensive F/W mounding, unable to achieve crossfalls or gradients by surfacing over | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
ALBANY ROAD | O/S 45, (opp 40) | Tilia x europea | Kerbs displaced/tipped by buttress root pressing immediately behind, cannot repair to standard | Engineering Solutions. Reset Kerb | N/A | Kerb displaced. Not possible to realign as kerb pushed into channel at radii and overgrowing kerb: Recommend replacement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
ARGYLE ROAD | O/S 3/5 | Tilia x europea | kerbs disrupted, unable to work around | Engineering Solutions. Thinner Kerbs, Tree Pit | N/A | Kerb displaced. Kerb pushed out of line by roots in channel and tracing to wall: Ramp would cause backfall to property: recommend replacement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
ARGYLE ROAD | o/s 11-13 | Tilia x europea | rooting above tarmac in f/w, cannot surface over, remains as trip hazard | Engineering Solutions. Root Pruning | N/A | Footway damaged. Roots in footway and carriageway ramp would be to severe: recommend replacement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BINFIELD ROAD* | just below 14, (effectively at side of 241 Chesterfield Rd) | Fraxinus excelsior | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BINFIELD ROAD* | o/s 6 | Acer pseudoplatanus | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BINFIELD ROAD* | s/o 1 burcot street, (adjacent/next to 19) | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BINFIELD ROAD* | Outside 29 (house on corner Ches Rd) | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
BINFIELD ROAD* | o/s 3-5 | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. Thinner Kerbs | N/A | Kerb displaced. Kerb pushed into carriageway: Roots beneath carriageway therefore unable to provide thinner kerb: recommend replacement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
HOLLYTHORPE CRESCENT | o/s 12 | Acer platanoides | TR: Felling - Footway damaged by shallow roots | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
HOLLYTHORPE CRESCENT | o/s 5 | Acer platanoides | TR: Felling - Footway damaged by shallow roots. Moderate decline of canopy | Engineering Solutions. Root Examination | N/A | Minor decline. Footway ramped – minor. Roots tracing to property severe damage in footway and backfall to property. Recommend replacement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
HOLLYTHORPE CRESCENT | o/s 16 | Acer platanoides | TR: Felling - Footway damaged by shallow roots | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | o/s 10 | Tilia x europea | Kerb absent and rooting into c/w, f/w mounded - too steep to reprofile, road too narrow for build out | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | o/s 33 | Tilia x europea | Substantial C/W and kerb damage, (too narrow for build out) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | o/s 26 | Fraxinus excelsior | Extensive rooting in c/w and f/w uplifted, damaged, too narrow to build out, f/w too steep to mound/ramp | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | o/s 43 | Alnus cordata | Extensive rooting above tarmac in c/w/channel, cannot work round at all, (road too narrow for build out), c/w uplifted also | Retain Tree. Exceptional Circumstances | N/A | Consider exceptional solutions to retain tree. Italian alder – rare tree. Root in gutter. Roots under wall: Severe damage to channel: Recommend removal | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | o/s 21 | Tilia x europea | Extensive buttress rooting within c/w, edgins as kerbs now displaced, road too narrow to accommodate build out | Reinvestigate. Further Investigation | N/A | Investigate root pruning; if not possible remove and replace tree. Buttress root in carriageway and under wall . Kerb displaced. Root in carriageway and under wall and drive. unable to form kerb line Buttress exposed. If roots cannot be cut replacement recommended | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | opp 55 | Aesculus hippocastanum | Stem in C/W at 1m - obstructive and very poor structural condition, parting union at 3m - weeping fluid, stem failure/collapse foreseeable | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
KENBOURNE ROAD | adj 1 | Tilia x europea | Extensive buttress root in c/w - cannot work round - encroaching into c/w by up to 25% c/w width | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 20-22 | Tilia x europea | F/W mounded, drive x-over useless | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 4/6 | Tilia x europea | TR: Felling- damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 34 | Tilia x europea | No kerb, rooting into c/w | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 24 | Tilia x europea | F/W mounded, drive x-over useless, rooting above tarmac in f/w also | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 15 | Aesculus hippocastanum | TR: Felling, network damage | Engineering Solutions. Removal of Kerb | N/A | Kerb displaced – minor. Root damage – minor. Major root damage: Roots tracing under access road, wall: Recommend removal | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 5 | Aesculus hippocastanum | Very poor physiological condition, virtually no extension growth, very undersized and few buds, potential 3rd party wall damage | Engineering Solutions. Ramping, Monitor Tree | N/A | Tree infected with bleeding canker of horse chestnut – may recover. Footway lifted. Roots tracing to wall of property: Recommend removal | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 7 | Aesculus hippocastanum | kerbs displaced, historic root severance, topped, Pseudomonas syringae pv. Aesculi - poor specimen, impinging on driveway also | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 17a | Tilia x europea | TR: Felling, network damage | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
LISMORE ROAD | o/s 21 | Tilia x europea | F/W mounded, drive x-over useless | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-11
* Indicates War Memorial Street