## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
ALDAM ROAD | O/S 22 | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | Significant buttress root in carriageway. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
ALDAM ROAD | o/s 37 | Fraxinus excelsior | TR: Felling, damage to network | Engineering Solutions. | Footway lifted. Two radial cracks. | N/A | Roots showing & damaging footway. Roots tracing to property: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
ALDAM ROAD | o/s 25 | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | Footway obstructed and lifted. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
ALDAM ROAD | o/s 11 | Sorbus aucuparia | TR: Felling, dying/diseased, NOTE: sterilise tools after use | Remove and replace tree. | Tree in poor condition. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 85 | Tilia x europea | TR: Felling, damage to surface | Engineering Solutions. | Kerb missing. Carriageway damaged. | N/A | Severe root damage in carriageway and displacement of kerb: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 87 | Acer pseudoplatanus | TR: Felling, damage to surface | Remove and replace tree. | Reduced vitality. Kerb displaced. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 95 | Tilia x europea | TR: Felling, damage to surface | Engineering Solutions. | Kerb missing. | N/A | Roots in carriageway and roots tracing to wall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 97 | Acer pseudoplatanus | TR: Felling, damage to surface | Remove and replace tree. | Root in carriageway. Kerb displaced. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 105 | Tilia x europea | TR: Felling, damage to surface | Engineering Solutions. | Kerb missing. Footway minor lifting. Carriageway not damaged. | N/A | Roots in carriageway and roots in kerbline: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 106 | Acer pseudoplatanus | TR: Felling, damage to network | Remove and replace tree. | Kerb missing. Significant footway lifting. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 112 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | Kerb missing. Significant footway lifting. Driveway lifted. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 37 | Prunus serrulata | TR: Felling, damage to surface | Remove and replace tree. | Pruning wound at 3m torn down stem and decaying. Bacterial canker infection. Footway damaged. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 77 | Tilia x europea | TR: Felling, damage to surface | Engineering Solutions. | Kerb missing. Footway lifted. | N/A | Buttress and roots under carriageway. Roots tracing to wall. Tree partly obstructing drive: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
BANNER CROSS ROAD | o/s 79 | Acer pseudoplatanus | TR: Felling, damage to surface | Remove and replace tree. | Kerb missing. Significant footway and carriageway. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
CRUISE ROAD | O/S 48 | Prunus Kanzan | TR: Felling- decay | Remove and replace tree. | Several ganoderma brackets. Impact wound to primary limb at 2m decaying. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
CRUISE ROAD | O/S 56 | Prunus Kanzan | TR: Felling- damage to network | Remove and replace tree. | Footway damaged. Third party damage. Weak unions at c. 2m. Impact wound. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
CRUISE ROAD | O/S 17 | Prunus Kanzan | TR: Felling- damage to network | Engineering Solutions. | Radial cracking to footway on hill. | N/A | Overhanging carriageway. Roots tracing to property. Roots high in footway. Ramping would create severe crossfall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
CRUISE ROAD | O/S 74 | Prunus Kanzan | TR: Felling- decay | Remove and replace tree. | Ganoderma at base. Fungal brackets. Buttress root decaying | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
HOLDINGS ROAD | o/s 12 | Prunus sp | TR: Felling - Kerb displacement and shallow rooting in the footpath. | Remove and replace tree. | Buttress root overhangs carriageway – impact damage evident. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
HOLDINGS ROAD | o/s 7 | Prunus sp | TR: Felling - Kerb displacement and shallow root in footpath. | Engineering Solutions. | Kerb displaced. Footway damaged – minor. | N/A | Severe damage by roots in carriageway. Roots tracing to wall: Recommend Replacements | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
HOLDINGS ROAD | o/s 31 | Prunus sp | TR: Felling - Kerb displacement and shallow rooting in the footpath. | Remove and replace tree. | Kerb displaced. Footway damaged. Footway obstructed. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
LAVERDENE WAY | O/S 1-3 | Prunus Kanzan | TR: Felling- damage to network | Engineering Solutions. | Root damaging footway 2m from tree. | N/A | Severe root damage to footway. Roots tracing to property: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
PSALTER LANE | opposite/facing Clifford rd junction | Tilia x europea | TR: Felling, network damaged | Engineering Solutions. | Recent apparently satisfactory repair. | N/A | Re-shape tree pit: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
PSALTER LANE | o/s 100 | Tilia x europea | TR: Felling, network damaged | Remove and replace tree. | Tree overhangs carriageway at c. 1.2m. Impact wound at c. 2m. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
PSALTER LANE | At traffic light junction with Cowlishaw Rd, (next to 136) | Tilia x europea | TR: Felling, network damaged | Remove and replace tree. | Tree growing in carriageway. Location of tree adjacent to pedestrian crossing creates significant visibility hazard. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SEABROOK ROAD | o/s 65 stafford rd. | Acer pseudoplatanus | TR: Felling - Kerb displacement and surface cracks to footpath, suspect shallow rooting ( old fungi at the base cannot ID ) | Engineering Solutions. | Kerb displaced – minor. Minor cracks to footway. | N/A | Damaged kerbs and roots in kerbline. Roots also tracing under wall, slight cracks: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SEABROOK ROAD | o/s 3 | Acer pseudoplatanus | Damage to Surface | Engineering Solutions. | Footway damage – one minor crack. | N/A | Damaged kerb and roots in kerbline. Roots also tracing under wall with recent repairs carried out, further cracks: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SILVER HILL ROAD | s/o 22 Mylnhurst (1st tree on rd from Mylnhurst Rd) | Acer platanoides | TR: Felling, damage to network | Engineering Solutions. | Kerb missing. | N/A | Severe root damage to footway. Damage to carriagewayby buttress in channel. Damage to wall also roots tracing to gully: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SILVER HILL ROAD | o/s 29 | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | Significant root in carriageway. Significant footway lift. Carriageway lifted. Adjacent utility cover. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SILVER HILL ROAD | o/s 18 | Aesculus hippocastanum | No kerbs or radius, tree growing within c/w, cannot repair or work around at all | Engineering Solutions. | Kerb missing. Root in carriageway - minor. | N/A | Severe damage in carriageway by roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SILVER HILL ROAD | o/s 17 | Aesculus hippocastanum | TR: Felling, damage to network | Remove and replace tree. | Kerb missing. Root damaging footway. Carriageway damaged. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SILVER HILL ROAD | o/s 7-9 | Acer platanoides | TR: Felling, damage to network | Remove and replace tree. | Footway damaged on steep corner. Kerb missing. Telegraph pole at 0.8m. Utility cover. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SUNNYVALE ROAD | O/S 98 | Prunus Kanzan | TR: Felling - Damage to Structures | Engineering Solutions. | Footway lifted – minor. Minimal footfall. | N/A | Damaging roots in footway. Buttress on edge of verge. Roots under wall showing slight cracks, slight lean into carriageway: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
SUNNYVALE ROAD | O/S 94 | Prunus Kanzan | TR: Felling - Damage to Structures | Remove and replace tree. | Third party damage. Footway lifted. Minimal footfall. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THOMPSON ROAD | O/s Yankees, 2nd tree from bottom | Tilia x europea | Extensive kerb disruption, cannot instal kerb at all, damaging C/W also | Engineering Solutions. | Kerb damaged. | N/A | Setts lifted in channel by roots. Roots also across footway tracing into private access and wall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THOMPSON ROAD | O/s 6 | Tilia x europea | Rooting between kerbs into c/w, cannot reset kerb, no other viable option but remove and replace | Engineering Solutions. | Root between kerb. Kerb is already very low along this section of the street. | N/A | Kerb displaced by buttress in kerbline with roots in channel. Roots also tracing to property: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THOMPSON ROAD | O/s 9, side of 1 Khartoum Road | Tilia x europea | Kerb lifted, kerb absent, and flagstones extensively lifted/displaced | Remove and replace tree. | Kerb damaged. Flagstone footway lifted and in very poor condition for full length of this section of the street. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
THOMPSON ROAD | Facing 15 at entrance to Botanics | Tilia x europea | Substantial rooting between kerbs, uplifting c/w, kerbs damaged, flags lifting, cannot sensibly repair | Remove and replace tree. | Substantial damage to kerb and footway. Adjacent gully. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
TYLNEY ROAD | o/s 7 | Acer pseudoplatanus | TR: Felling loss of kerb alignment and footpath cracking - suspect shallow roots. Basal decay. | Engineering Solutions. | Basal cavity and decay – healing. Minor damage to kerb and footway. | N/A | Monitor Stihl Saw repair as temporary measure: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-22
TYLNEY ROAD | o/s 26 | Gleditsia triacanthos 'Sunburs | TR: Felling - surface cracks in footpath, suspect shallow roots. | Engineering Solutions. | Three cracks to footway. | N/A | Damage to footway by roots longitudinal. These are now becoming severe: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
TYLNEY ROAD | o/s 35 | Celtis australis | TR: Felling - Senescent | Remove and replace tree. | Dead. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
TYLNEY ROAD | o/s 10 | Celtis australis | TR: Felling: Failure | Remove and replace tree. | Dead. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
TYLNEY ROAD | o/s 58 | Gleditsia triacanthos 'Sunburs | TR: Felling - large surface crack- suspect shallow rooting in foorpath. | Remove and replace tree. | Significant damage to footway. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
TYLNEY ROAD | o/s 19 | Acer pseudoplatanus | Damage to Surface | Remove and replace tree. | Footway damaged – significant. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | o/s 55-57 | Acer platanoides | TR: Felling, damage to network, damage to structures | Engineering Solutions. | Root in channel. Kerb missing. No sign of third party damage. | N/A | Roots in carriageway and footway. Roots tracing to wall, slight cracks starting to show: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | o/s 39A, OPPOSITE 26 | Acer platanoides | TR: Felling, damage to network, damage to structures, c/w encroachment | Remove and replace tree. | Footway lifted. Kerb displaced. Tree overhangs carriageway at 2m. Impact wound at 2.5m. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | o/s 45 | Acer platanoides | TR: Felling, damage to network, damage to structures | Remove and replace tree. | Root between kerbs. Footway lifted - significant. No sign of third party damage. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | o/s 49 | Acer platanoides | TR: Felling, damage to network, damage to structures | Remove and replace tree. | Kerb displaced – minor. Footway lifted – significant. Third party damage. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | s/o 185 Millhouses Lane (last tree on rd) | Acer platanoides | TR: Felling, damage to network | Remove and replace tree. | Significant root in carriageway. Footway lifted. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | o/s 75-77 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | Extensive damage to footway. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | o/s 79 | Acer platanoides | TR: Felling, damage to network | Remove and replace tree. | Significant root between kerbs. Significant footway lift. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22
WHIRLOWDALE CRESCENT | s/o 185 Millhouses Lane, (second tree from end of road) | Acer platanoides | TR: Felling, damage to network | Remove and replace tree. | Kerb displaced. Significant root in carriageway. | N/A | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-22