## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
Chelsea Road | o/s 2 | Platanus x hispanica | Kerbs displaced, f/w and c/w uplifted, will be damaged upon reconstruction | Remove and Replace | The two trees are in good condition and have good life expectancy. We advise that there is no arboricultural need to remove these trees. We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree outside number 2 is a London Plane. It is causing significant disruption to the pavement, and some disruption to the kerb. There is an adjacent gully and a utility cover. We do not believe this disruption can be acceptably resolved. We therefore advise that this tree should be removed and replaced. | N/A | Continue with tree replacement as planned. | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17
Chelsea Road | adj/side of 111 UNION RD | Ulmus procera | Rooting above tarmac in carriageway, completely unable to work round without severing roots | Engineering Solutions | We have therefore considered whether there are engineering solutions that would prevent the need for removal and replacement of these trees. The tree adjacent to number 111 Union Road is a Huntingdon Elm (and not an English Elm), a notable and rare species, which we advise there is a strong arboricultural case to retain. The tree is causing some disruption to the pavement, and to the carriageway, where there are numerous utility covers. We nevertheless believe that a combination of engineering solutions could be used to retain this tree, install dropped kerbs, and render the pavement and carriageway satisfactory and safer at all parts of the Chelsea Road and Union Road junction. We recognise that this may incur additional costs. We therefore advise the Council to reconsider its plan for this tree with a view to retaining it. | N/A | The roots are under the carriageway therefore solution would be expensive if retained: Recommend Replacement | Continue with tree replacement as planned. | Replace Tree as Planned | Paul Billington |  | 2017-05-17