## Council Decision
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
BURNGREAVE STREET | O/S 44 | Tilia sp | TR: Felling - Kerb displaced by buttress. Shallow roots damaging dropped crossing. | Engineering Solutions. | Excavate to consider scope for root pruning. Redo dropped kerb. |  | Roots tracing into garage gate area and damaging crossing. Redo dropped kerb not feasible. Also causing partial obstruction. Roots also in carriageway under. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
BURNGREAVE STREET | O/S 17-19 | Fraxinus excelsior | Poor Structural Condition (TR: Felling-) | Retain Tree. | None | ITI | Severe root damage to footway, kerb line. Roots under carriageway lifting and also tracing to rear wall: No Engineering solutions suggested by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 39 - 41 Norfolk park avenue | Prunus sp | TR: Felling Root decay | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 91 Norfolk park avenue | Prunus sp | TR: Felling - Basal decay, included union and shallow rooting in the footpath. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 23 Norfolk park avenue. | Prunus sp | TR: Felling - Large root in footpath. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 33 | Prunus sp | TR: Felling-Damage to Surface, shallow rooting in footpath. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 35 | Prunus sp | TR: Felling- Shallow rooting in footpath, stem exudation. | Retain Tree. | None | ITI | Roots under wall and damaging crossing. No Engineering comments by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 55 Norfolk park avenue | Sorbus aucuparia sp | TR: Felling-Dead | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 39 | Prunus sp | TR: Felling-Damage to Surface. Rooting in footpath and root decay. Included union at 1m. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 51 Norfolk park avenue | Prunus sp | TR: Felling-Damage to Surface - shallow rooting in footpath, basal decal and included union. | Engineering Solutions. | Repair footway. | ITI | Roots under wall same as o/side No 35 Ramping would cause backfall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 21 Norfolk park avenue. | Prunus sp | TR: Felling - Significant wild rooting, some root decay. Suspect shallow rooting. | Engineering Solutions. | Resurface footway. |  | Surface over footway as temporary measure: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | Adjacent 5 Donnington road. | Prunus sp | TR: Felling_ Root decay and surface rooting in footpath, stem cavity. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 33-31 Norfolk park avenue | Prunus sp | TR: Felling Cavity at the stem base and weak/included union. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 37 | Prunus sp | TR: Felling-Damage to Surface - large surface root. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
DONNINGTON ROAD | o/s 83 Norfolk park avenue. | Prunus sp | TR: Felling Buttress root in footpath, exposed decayed root and weak unions at crown break. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
LEIGHTON ROAD | opp 76 | Acer platanoides | TR: Felling - Footway damage, shallow rooting in the footway. | Engineering Solutions. | Repair and ramp footway. |  | Severe Roots in Footway tracing into garden. Ramping would increase fall and not address problem: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
LEIGHTON ROAD | opp 52 | Fraxinus excelsior | TR: Felling Footway damage - shallow roots in footway. | Engineering Solutions. | Repair and ramp footway. |  | Severe Roots in Footway tracing into garden: Ramping would increase fall and not address problem: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
LEIGHTON ROAD | Adjacent 108 rear garden. | Acer pseudoplatanus | Flags displaced by shallow roots. Suspect shallow roots within footway. (TR: Felling-) | Retain Tree. | None |  | Slight roots lifting recent bitmaced repair on flags. Crossing slightly obstructed: Roots observed in garden and between rear of flags and wall. No Engineering solutions by ITP: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRABTREE CLOSE | o/s 109-111 | Malus sylvestris | Structural Integrity compromised (TR: Felling-) | Engineering Solutions. | Remove Limb | ITI | ITI verifies 100mm decay into 145mm stem: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRABTREE CLOSE | o/s 115 | Malus sylvestris | Structural Integrity compromised (TR: Felling-) | Retain Tree. | None | ITI | Ramp Over as temporary measure: Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-29
CRABTREE CLOSE | junc w/Crabtree ave | Tilia x europea | Carriageway Obstruction (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRABTREE CLOSE | o/s 97 | Malus sylvestris | Structural Integrity compromised by decay fungus at crown break. (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 80 | Fraxinus excelsior | TR: Felling, damage to f/way | Engineering Solutions. | Remove Kerb |  | Existing thin kerb already showing signs of movement. Further ramping would add additional pressures to bowed 3rd party wall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 50 | Fraxinus excelsior | TR: Felling, damage to f/way | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 41 | Tilia x europea | Extensive kerb damage | Engineering Solutions. | Remove Kerb |  | Severe root damage pushing out kerb and tracing under carriageway and wall: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 34 | Platanus x hispanica | extensive damage to footway and kerb | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 45/47 | Sorbus aria | structural integrity (TR: Felling-) | Engineering Solutions. | Larger Tree Pit |  | Minor roots tracing towards wall, surface footway: Retain Tree and monitor | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 85 | Sorbus aria sp | TR: Felling, damage to f/way | Engineering Solutions. | Remove Kerb |  | Ramping limited due to other thresholds. Thin kerb option not possible: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 77 | Tilia x europea | TR: Felling, damage to f/way | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 83 | Tilia x europea | TR: Felling, damage to f/way and kerbstone missing | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | s/o 129a | Fraxinus excelsior | TR: Felling - Damage to Surface/Structures | Engineering Solutions. | Larger Tree Pit |  | Kerb uplifted, possible root in cway. Damaged 3rd party wall repaired, extend tree pit and tarmac around: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 61 | Tilia x europea | Kerbs displaced and footway uplifted - cannot repair adequately without tree removal | Engineering Solutions. | Thinner Kerb, Ramping |  | Damage to rear concrete drive and causing obstruction which may incur strikes recommend replacement away from access: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 64 | Prunus sp | Kerbs displaced and weak unions at crown break, poor specimen | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRAWFORD ROAD | o/s 58-60 | Tilia x europea | TR: Felling, damage to f/way | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRESCENT ROAD | o/s 81 | Tilia x europea | Basal Ganoderma sp. fungal fruiting body, heartwood decaying | Retain Tree. | None | ITI | Roots under wall [previously repaired] carriageway and footway pushed out: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRESCENT ROAD | o/s 36-38 | Acer pseudoplatanus | Significant basal cavity, poor structural condition | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
CRESCENT ROAD | o/s 10 | Platanus x hispanica | Rooting over kerb into carriageway - cannot work around, c/w incursion at 1.7m also, obstructive | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
HAMPTON ROAD | o/s 37 | Tilia x europea | TR: Felling - previously topped (Structural Integrity compromised); minor f/way and kerb displacement. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
HAMPTON ROAD | opp 3 | Carpinus betulus | TR: Felling - kerb and footway disruption (realignment of kerb unlikely without significant damage to roots); major limb obstructing carriageway - removal of limb not an option. | Engineering Solutions. | Tree Pit, Remove Limb | ITI | This can be resolved by extending tree pit: Retain Tree and monitor | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-29
HAMPTON ROAD | o/s 40 | Acer pseudoplatanus | TR: Felling - significant footway uplift; kerb displaced due to buttress - no scope to install full profile kerb. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
HAMPTON ROAD | o/s 56 | Tilia x europea | TR: Felling - Kerb missing, no scope to replace due to buttress. Significant footway uplift. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
HAMPTON ROAD | adj. 23 Fir Vale Road | Sorbus aria | TR: Felling - co-dominant stems with included-bark. Bark/Stem wounds with decay. | Retain Tree. | None | ITI | This can be ramped successfully: Temporarily Retain Tree | Retain Tree | Retain Tree | Paul Billington |  | 2017-06-29
HAMPTON ROAD | o/s 32 | Platanus x hispanica | TR: Felling - significant kerb and footway disruption; damage to 3rd party wall. | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | o/s 11/13 | Prunus avium | TR: Felling - Crown approx. 50% dead | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | adj. 225 Barnsley Road (nearest to junct.) | Acer pseudoplatanus | TR: Felling - severe f/way uplift | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | o/s 22/24 | Pyrus communis | TR: Felling - significant f/way and kerb disruption; 50% of crown removed (unauthorised) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | s/o 227 Barnsley Road | Acer pseudoplatanus | TR: Felling - Structural Integrity; significant f/way uplift | Retain Tree. | None | ITI | Tree in a poor and declining condition with no prospect of recovery: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | O/S 10 | Prunus sp | TR: Felling - poor physiological condition (resulting from unauthorised pruning) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | adj. 227 Barnsley Road | Acer pseudoplatanus | TR: Felling - poor physiological condition; several cavities (branch sockets) with high likelihood of development of coalescent decay. | Remove and replace tree. | None | ITI | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | O/S 29 | Prunus sp | TR: Felling - damage to 3rd party boundary wall; significant f/way disturbance | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
FIRSHILL AVENUE | opp. 5 | Acer pseudoplatanus | TR: Felling - significant f/way and kerb disruption | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
GREEN OAK ROAD | O/S 121-123 | Prunus Kanzan | TR: Felling- structurally poor | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
GREEN OAK ROAD | O/S 126-128 | Prunus Kanzan | TR: Felling- damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
GREEN OAK ROAD | O/S 108-106 | Prunus Kanzan | TR: Felling- decay | Retain Tree. | None | ITI | Examination shows advanced decay at ground level: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
GREEN OAK ROAD | O/S 129-131 | Prunus Kanzan | TR: Felling- decay | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SILVERDALE CLOSE | s/o 40 Silverdale Rd | Prunus Amanogawa | TR: Felling - Dead | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SILVERDALE CLOSE | o/s 23 | Prunus Amanogawa | F/W lifted and rooting above tarmac level in f/w | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SILVERDALE CLOSE | o/s 9 | Prunus serrulata | TR: Felling, decay | Retain Tree. | None | ITI | Crown in advanced stage of break-up, no prospect of recovery: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SILVERDALE CLOSE | o/s 12 | Prunus serrulata | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SILVERDALE CLOSE | O/S 25 | Prunus Amanogawa | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SKIPTON ROAD | o/s 22 | Prunus x yedoensis | Poor Structural Condition (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned. | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29
SKIPTON ROAD | o/s 24 | Prunus sp | Poor Structural Condition (TR: Felling-) | Retain Tree. | None | ITI | The canopy has a poor foliage density and low vigour and decay in the roots: Recommend Replacement | Continue with replacement | Replace Tree as Planned | Paul Billington |  | 2017-06-29