## Sheet1
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date Released
THORNSETT ROAD | At side of 22 PRIORY ROAD, on Thornsett rd. | Tilia x europea | Symptoms consistent with Phytophthora infection. | N/A - see Streets Ahead response | N/A |  | This tree was not identified for replacement prior to the ITP process, as at previous routine inspections did not show its current state. Recent inspections have led to this tree being identified with symptoms consistent with Phytophthora infection. Recommend replacement. | Replace tree, noting that this is a condition replacement, recently identified and has not been through the ITP process as that has now finished. | Replace Tree | Paul Billington |  | 2017-07-31
THORNSETT ROAD | At side of 33 Priory Rd but ON Thornsett Rd | Acer pseudoplatanus | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb |  | Root buttress in carriageway at radii, unable to reset of build out. Roots Tracing to wall also. Recommend replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | Facing 34, on corner/radius of junction into Agden rd. | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb |  | Thin kerb not possible due to root presence. Could consider leaving some kerbs out instead but during investigations into the possibility of implementing the ITP advice it was found that the tree has indications of Phytophthora sp. Infection and so to prevent further spread into adjacent trees, which are predominantly lime and so susceptible the tree requires removal. Recommend replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 1, (second tree up from junction Kenwood Pk Rd) | Platanus x hispanica | TR: Felling, damage to network | Engineering Solutions. | Remove Kerb, Root Pruning |  | Roots tracing to wall. Buttress in channel / kerb line so unable to provide thin kerb. Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement. Recommend replacement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 14 | Tilia x europea | Symptoms consistent with Phytophthora infection. | N/A - see Streets Ahead response | N/A |  | This tree was not identified for replacement prior to the ITP process, as at previous routine inspections did not show its current state. Recent inspections have led to this tree being identified with symptoms consistent with Phytophthora infection. Recommend replacement. | Replace tree, noting that this is a condition replacement, recently identified and has not been through the ITP process as that has now finished. | Replace Tree | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 2, (middle 1 of 3 at side of 2-2a) | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb |  | Half width kerb recommended. Temporarily retain tree. | Retain Tree | Retain Tree | Paul Billington |  | 2017-07-31
THORNSETT ROAD | At side of 22 Priory Road, on Thornsett Road (Shown as O/S 22 on ITP letter) | Acer pseudoplatanus | TR: Felling, damage to network | Reinvestigate. | Root Pruning |  | Two trials by Streets Ahead involving exposing roots of street trees have shown that root pruning and root bending of mature trees is not a viable practical option to retain a tree. Also a 1998 Sheffield based study and investigation by Nicoll and Armstrong published in the International Journal of Urban Forestry shows this advice around root pruning to be impossible to implement. Recommend replacement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 23 | Aesculus hippocastanum | TR: Felling, damage to network | Engineering Solutions. | Square off Driveway |  | Roots are showing slightly beneath crossing and due to the proximity to the stem, size of lateral roots and likely large extent of root system effected root pruning is not possible. Also the tree is now in declining health Recommend replacement | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 3 | Acer pseudoplatanus | TR: Felling, damage to network | Engineering Solutions. | Thinner Kerb |  | Roots tracing to wall. Buttress in channel / kerb line so unable to provide a thinner kerb. Recommend replacement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 3, just downhill of driveway for 1 | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 33A | Tilia x europea | TR: Felling- carriageway obstruction | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 4, (bottom side of Bridge Club Carpark) | Tilia x europea | TR: Felling, damage to network | Engineering Solutions. | Remove Kerb |  | Roots under channel at gully side. Damage evident from roots tracing into wall and access. Recommend replacement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 40 | Tilia x europea | Rooting into c/w, no kerbs and extensive stem exudation consistent with Armillary infection | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 5a | Platanus x hispanica | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 6, o/s bridge club | Platanus x hispanica | Buttress in carriageway (TR: Felling-) | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 7a | Acer pseudoplatanus | TR: Felling, damage to network | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31
THORNSETT ROAD | O/S 9 | Aesculus hippocastanum | TR: Felling, Base decaying and physiologically poor | Remove and replace tree. | None |  | Continue with tree replacement as planned | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-07-31