## Proposed Headings
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date
BRACKEN ROAD | o/s 115 | Fraxinus excelsior | Poor Structural condition - previously topped. Large cavity @ 4m. (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
CAMBORNE ROAD | side of - rear of 21 Aysgarth Road (tree on Camborne Rd) | Tilia x europea | Kerbs displaced and f/w uplifted - unable to rectify without unacceptable root damage | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
CHEADLE STREET | o/s 1 | Acer pseudoplatanus | TR: Felling, carriageway obstruction | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
CHEADLE STREET | side of 8 hawksley road | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
CHERRY BANK ROAD | o/s 48 | Prunus avium | Shallow roots damaging footway. Root prune not viable. (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
DOROTHY ROAD | o/s 24 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
FIR STREET | opp 41 (top of road) next to road width sign | Acer pseudoplatanus | TR: Felling: Damage to Structures | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
FIR STREET | o/s 41 (top of road) next to road width sign | Fraxinus excelsior | Self set, inappropriate location. Will obstruct traffic and damage retaining wall when mature. (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
HILLCREST ROAD | O/S 45 | Prunus Kanzan | F/W uplifting, recent patch repair inadequate solution for long term | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 19 (immediately topside of driveway) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 49 | Tilia x europea | TR: Felling, damage to network, and obstructive | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 47 ("Ashburnam") | Tilia x europea | TR: Felling, damage to network, and obstructive | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 43 (topside outside 43) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 41-43 (between the 2) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 41 (topside of 41 driveway) | Tilia x europea | TR: Felling, damage to network, possibly obstructive | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 23-25 (on corner of driveway) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date
KENWOOD PARK ROAD | O/S 37-39, bottomside driveway | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 33, OPPOSITE 26 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 31, (opposite 24) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 45, centrally | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 15, lowermost side of driveway | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 51 | Tilia x europea | TR: Felling, damage to network, and obstructive | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 13 (lowermost side o/s 13) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD PARK ROAD | O/S 28 "The Workshop", (bottomside driveway) | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 16 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 16 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s hotel gates (opp 42, at gated entrance to hotel) | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 16 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 42 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 11 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 3 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 12 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 8 (OPPOSITE 7) | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
KENWOOD ROAD | o/s 16 | Tilia x europea | TR: Felling, damaging network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
Street | Tree Location | Tree Species | Primary reason for tree being identified for replacement | Summary of ITP Advice | Other Party Consulted | Streets Ahead Response | Streets Ahead Proposal | Final Decision | Decision Maker | Signature | Date
NETHER LANE | opp. 20 | Acer pseudoplatanus | inappropriate location - likely to damage property (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
NETHER LANE | opp. jnct. Johnson Lane | Acer pseudoplatanus | Poor Structure / Inappropriate Location (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
NETHER LANE | opposite jnct. Johnson Lane | Acer pseudoplatanus | Poor Structure / Inappropriate Location (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
NETHER LANE | opp. r/o 14-16 Mellor Lea Farm Garth | Acer pseudoplatanus | Poor Structure / Inappropriate Location (TR: Felling-) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
STANLEY ROAD | o/s 14/16 | Tilia x europea | Extensive kerb disruption - root pressure immediately behind, stem encroaching C/W, obstructive also | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
STANLEY ROAD | o/s 22 | Tilia x europea | Kerb displaced, unable to reset - rooting immediately behind | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
STANLEY ROAD | o/s 15, (opp 24) | Tilia x europea | F/W narrowed, less than 800mm clearance (approx) | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
STANLEY ROAD | between 11-15 | Tilia x europea | Kerb displaced and f/w ramping unnacceptably steep | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
STANLEY ROAD | Side of 22 Meersbrook Rd, at bottom Stanley Rd (o/s green wooden gates) | Tilia x europea | Kerb damaged and f/w uplifted | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
STANLEY ROAD | facing 37 meersbrook road (bottom of Stanley Rd) | Aesculus hippocastanum | Kerbs absent, f/w damaged and rooting into c/w, cannot work around | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06
WOSTENHOLM ROAD | O/S 65 | Tilia x europea | TR: Felling, damage to network | Remove and replace tree. | N/A | ITP, SCC and Amey in agreement. | Continue with tree replacement as planned. | Replace tree as planned | Paul Billington |  | 2017-04-06